## Profile
Farm 366, 369 and 368/2 Jeeptrack, Trail and Footpath network
Trail segment profiles and IAP observations
Cumulative until 2023-05-06
HC Eggers
| Route code | Location | Type | Slope | Minimum Width (metres) | Maximum Width (metres) | Erosion status | Current Usage | Current Management Status | Responsible Party | Future Management Status | Rehabilitation / Closure Priority | On trailforks | On alltrails | HCE kml file | Date of assessment | Photo Codes | No. of Photos | Comments
| V0063 | Connector plantation to V0064 | B | 3 | 1 | 1 | [9 empty] | 221120 | aa through |  | Misnomer;this is a bicycle track. Main route managed by STF
| V0063 | Connector plantation to V0064 | B | 3 | 1 | 1 | [9 empty] | 221120 | to am |  | Erosion not attended to by STF
| V0036 | Upper plantation | V | [12 empty] | 221120 | an ao |  | Photos from Origin of Trails race
| V0050 | Gate-clubhouse | V | 1 | 3 | 4 | 3 | 3 | W | M | O | 2 | 1 | 1 |  | 230105 |  | 5 | Main road to clubhouse, bad erosion, needs MOUNDS, not SCRAPING
| V0039c | Clubhouse to NE | V | 2 | 3 | 4 | 3 | 3 | W | M | O | 1 | 1 | 1 |  | 230105 |  | 3 | Lower part near V0034 urgently needs erosion work
| V0032 | Upper plantation | V | 2 | 3 | 3 | 3 | 3 | W | M | O | 2 | 1 | 1 |  | 230105 |  | 1 | Top badly eroded and wide, 4x4 only, used by mtb as uptrail
| B0093 | V0050 to clubhouse “Eden Mainline” | B | 1 | 2 | 3 | 2 | 3 | W | F | O | 1 | 1 | 1 |  | 230105 |  | 0 | Trail keeps getting wider and deeper, not sustainable
| B0097 | Upper part of “Forbidden Fruits” | B | 2 | 1 | 2 | 3 | 2 | L | M | C | 2 | 0 | 0 |  | 230105 |  | 3 | Illegal route, closing is important
| H0001 | Plantation E to Pyramid | H | 3 | 1 | 1 | 3 | 2 | W | M | R | 2 | 0 | 1 |  | 230105 |  | 0 | Erosion urgently needs attention
| H0002 | Pyramid upper fynbos | N | -- | 0 | 0 | 0 | 0 | C | M | N | 0 | 0 | 0 |  | 230105 |  | 0 | H0002 does not exist
| H0003 | Upper fynbos to Schuilplaats kloof | H | 2 | 1 | 1 | 2 | 1 | W | M | R | 1 | 0 | 1 |  | 230105 |  | 0 | Segment around kloof in bad shape. Bark stripping. Litter
| V0037 | F369 lower | V | 1 | 2 | 2 | 2 | 3 | W | M | O |  |  |  |  | 230226 | aa ab ac ad ae | 5 | Leaning pines, dangerous (aa ab ac ad ae)
| B0070 | Footpath east of waterworks | H | 3 | 0 | 2 | 3 | 2 | W | M | R | 2 |  |  |  | 230226 | af an ao |  | Significant erosion (af an ao)
| V0034 | Main contour connector to waterworks | V | 0-2 | 3 | 3 | 0-3 | 3 | W | M | R | 2 |  |  |  | 230226 | ag ah ai |  | Corner V0034 unusable for vehicles! (ag ah ai)
| V0034 | Main contour connector to waterworks | V | 0-2 | 3 | 3 | 0-3 | 3 | W | M | R | 0 |  |  |  | 230226 | aj ce |  | A saligna and kikuyu infestation along borehole site (aj) bad A melanoxylon (ce)
| V0021 | Back entrance to waterworks | V | 0 | 3 | 3 | 0 | 3 | O | M | O | 0 |  |  |  | 230226 | ak |  | A saligna infestation (ak)
| V0053 | Waterworks enclosed dams | V | 0 | 1 | 1 | 0 | 1 | O | M | O | 0 |  |  |  | 230226 | al am |  | Heavy IAP infestation around dams (al, am)
| V0033 | Waterworks east along Schuilplats | V | 2 | 2 | 2 | 2 | 1 | W | M | W | 1 |  |  |  | 230226 | ap aq ar |  | A melanoxynon infestations and regrowth (ap aq ar)
| not on TMP | From V0033 southwards | H | 1 | 0 | 1 | 0 | 0 | L | M | C | 0 |  |  | 230226-1501 | 230226 |  |  | Fragments of footpath across Schuilplaats river to oak trees
| V0024 | Waterworks east (upper part) | V | 2 | 3 | 3 | 1 | 3 | O | M | O | 1 |  |  |  | 230226 | as at |  | Needs proper berms (as at)
| FID288 | Connector V24 to V19 | V | 2 | 3 | 3 | 0 | 3 | O | [6 empty] | 230226 | au |  | Gravel put down (Pau)
| V0026 | Connector V24 to V26 | V | 0-1 | 3 | 3 | 1-2 | 3 | [7 empty] | 230226 | av |  | Thin gravel with eroson on edge (av)
| FID282/FID283 | Eastern edge of eucalyptus row | V | 3 | 3 | 3 | 3 | 2 | [7 empty] | 230226 | aw ax |  | Erosion (aw ax)
| FID283/FID282 | Eastern edge of eucalyptus row | V | 3 | 3 | 3 | 3 | 2 | [7 empty] | 230226 | aw ax |  | Erosion (aw ax)
| V0013 | Top contour connector to Coetzen | V | 2 | 3 | 2 | 3 | 3 | [7 empty] | 230226 | ay az |  | Erosion (ay) eucalyptus (az)
| not on TMP | V0017 – V0016 – V0013 | V | 2 | 2 | 3 | 3 | 1 | L | M | C | 2 |  |  | 230226-1545 | 230226 | ba bb bc bd be |  | Jeep track made by invasives contractors (erosion ba, bb, bc) (IAPs bd be)
| V0014 | E Brandwacht suburb V0012 – V0013 | V | 2 | 2 | 3 | 3 | 1 | ? | M | ? | 1 |  |  | 230226-1607 | 230226 | bi |  | Jeep track made by invasives contractors erosion Pbi
| V0013 / B0068 | Junction | V/B | 0-1 | 2 | 2 | 3 | 3 |  | F |  |  | 1 |  |  | 230226 | bf bg |  | erosion on V0013 (bf bg)
| B0068 / V0013 | Junction | V/B | 0-1 | 2 | 2 | 3 | 3 |  | F |  |  | 1 |  |  | 230226 | bf bg |  | erosion on V0013 (bf bg)
| V0013 | Northernmost part | V |  |  |  | 0 | 3 | N/A | M |  |  | 1 |  |  | 230226 | bh bm bn |  | IAP hakea large (bh bm bn)
| V0011 upper | Down from V0017 | V |  |  |  | 0 | 2 | N/A | M | [5 empty] | 230226 | bj bk bl br bs bt |  | IAP fresh foliar spraying (bj bk bl) markings (br bs bt)
| V0011 lower | Down, then contour to V0019 | V | 1 | 2 | 2 | 3 | 2 |  | M | [5 empty] | 230226 | bo bp bq |  | Bad erosion (bo bp bq)
| V0011 | E Brandwacht suburb V0019 – V0007 | V | 1 | 2 | 3 | 2 | 1 | 2 | M | ? | 1 |  |  | 230226-1617 | 230226 | bu bv bw bx by bz |  | Connector downwards and then contour, erosion (bu), opuntia (bv bw), amaryllis (bx), eucalyptus (by), pennisetium (kikuyu) (bz)
| V0019 | E Brandwacht suburb | V | 1 | 3 | 3 | 1 | 2 | [6 empty] | 230226-1619 | 230226 | ca cb cc |  | Mild erosion (ca cc) A saligna (cb)
| V0020 upper | F369 norther border | V | 2 | 3 | 4 | 1 | 1 |  | M | [5 empty] | 230226 | cd |  | Gravel, inadequate berms (cd)
| v0050b | Gate-clubhouse lower | V | 1 | 3 | 3 | 3 | 3 | [7 empty] | 230319 | aa ab ac |  | Main road to clubhouse, bad erosion, needs MOUNDS, not SCRAPING
| V0051 | short connector V0050 FID087 | V | 1 | 3 | 3 | 3 | 3 | [7 empty] | 230319 |  |  | Main road to clubhouse, bad erosion, needs MOUNDS, not SCRAPING
| FID087 | Main road up to clubhouse | V | 2 | 4 | 4 | 3 | 3 | [7 empty] | 230319 | af ag ah ai |  | Main road to clubhouse, bad erosion, needs MOUNDS, not SCRAPING
| FID087 | Area F | V | 1 | 1 | 1 | 1 | 0 | [7 empty] | 230319 |  |  | Biomass still not removed; truck and excavator tracks, Red Data species
| V0064 | Main road along fence | V | 1 | 3 | 3 | 2 | 3 | [7 empty] | 230319 |  |  | Sheet erosion everywhere, main connector must have PRIORITY
| V0065 | Left branch off V0064 | V | 2 | 1 | 2 | 2 | 2 | [7 empty] | 230319 | aj ak am |  | Road is closing up due to fynbos overgrowth
| B0139 | Mainline bike connector | B | 3 | 1 | 1 | 2 | 3 | [7 empty] | 230319 | am |  | Main connector, STF responsibility, no maintenance
| V0066 | Upper connector to fynbos H0004 | V | 3 | 1 | 2 | 2 | 2 | [7 empty] | 230319 |  |  | Eroded in parts
| V0056 | Steep upper part of former gumline | H | 3 | 2 | 2 | 2 | 1 | [7 empty] | 230319 | an ao |  | Recovering but some erosion (2011 FSM rehabilitation project)
| H0004 | Main fynbos footpath | H | 1 | 1 | 1 | 1-3 | 3 | [7 empty] | 230319 | ap |  | Earlier effective measures by STF, not maintained
| H0004 | Main fynbos footpath | H | 1 | 1 | 1 | 1-3 | 3 | [7 empty] | 230319 | as at au |  | Heavily used by runners and hikers. Wetlands part badly eroded
| F366 Fynbos | Sheepwalk slope north | [13 empty] | 230319 | aq ar |  | Dense and large Hakea invasion
| F366 Fynbos | North arm of Blouklip | [13 empty] | 230319 | av aw |  | Dense A. longifolia invasion inside riparian area
| v0050b | Gate-clubhouse lower |  |  | 4 | 4 | [9 empty] | 230425 | ab ac |  | Grader, widened to 4m, side disturbances
| FID86 | S border to smallholdings | [13 empty] | 230425 | ad |  | No grading, erosion
| B0125 | Circular loop in fynbos | [13 empty] | 230425 | ae |  | Deep furrow, should be closed
| V0050 branch | Gate left branch | [13 empty] | 230425 | af |  | Not named on kml file
| FID80 | Main road to dams etc | [13 empty] | 230425 | ag |  | Large puddle covering road, needs infill
| FID303 | Main road to dams etc | [13 empty] | 230425 | ag |  | Same as FID80! Becomes V0044. Large puddle covering road, needs infill
| V0047 upper | branches off from V0044/FID80 |  |  | 4 | 4 | [9 empty] | 230425 | ah |  | Grader, widened to 4m, side disturbances
| B0126 | branches off from V0044/FID80 | [13 empty] | 230425 | ah |  | Now full-sized jeep track, must be renamed V
| V0040 lower | Jeeptrack east/upwards | [13 empty] | 230425 | ai |  | Map is missing lowest part of this jeep track. Grading
| V0040 lower | Jeeptrack east/upwards | [13 empty] | 230425 | aj
| V0043 | Junction | [13 empty] | 230425 | ak |  | Grader, side disturbances, muddy due to scraped vegetation
| V0044 | Junction |  |  | 4 | 4 | [9 empty] | 230425 | ak |  | Grader, widened to 4m, side disturbances, muddy
| FID80 | Junction |  |  | 4 | 4 | [9 empty] | 230425 | ak |  | Grader, widened to 4m, side disturbances, muddy
| V0043 | Connector to dam lowerside |  |  | 4 | 4 | [9 empty] | 230425 | al am |  | Grader, widened to 4m, side disturbances
| V0043 | Connector to dam lowerside | [13 empty] | 230425 | an |  | A. melanoxynon infestation
| V0043 | Connector to dam lowerside |  |  | 4 | 4 | [9 empty] | 230425 | ao |  | Grader, widened to 4m, side disturbances
| V0037 | Connector to dam upperside | [13 empty] | 230425 | ap aq ar as at |  | Grader, deep side furrows, muddy due to scraped vegetation
| V0034 | Junction | [13 empty] | 230425 | au |  | Erosion fixed for the moment, road widened
| FID71 | Junction | [13 empty] | 230425 | au |  | Erosion fixed for the moment, road widened
| V0034 | NS jeep track above dams |  |  | 4 | 4 | [9 empty] | 230425 | av |  | Grader, widened to 4m, side disturbances
| V0034 | NS jeep track above dams | [13 empty] | 230425 | ax |  | Pampas grass infestation
| V0029 | V0034 eastwards along Schuilplaats |  |  | 4 | 4 | [9 empty] | 230425 | aw |  | Grader, widened to 4m, side disturbances
| V0033 | V0034 eastwards along Schuilplaats |  |  | 4 | 4 | [9 empty] | 230425 | ay az |  | Grader, widened to 4m, side disturbances
| V0054 | East of dam entrance | [13 empty] | 230425 |  |  | Does not exist
| FID136 | Off V0029 | [13 empty] | 230425 |  |  | Does not exist
| V0038 | Off V0029 | [13 empty] | 230425 |  |  | Does not exist
| FID291 | is a part of V0039c |  |  | 4 | 4 | [9 empty] | 230425 | bc |  | Grader, widened to 4m, side disturbances
| B0074 | connector V0039c, V0037 | [13 empty] | 230425 |  |  | Does not exist
| B0075 | connector V0039c, V0037 | [13 empty] | 230425 |  |  | Does not exist
| V0027 | cycle path connector | [13 empty] | 230425 | be |  | Not a jeep track, must be renamed to B, part of STF trail
| V0030 | Upper part of “Diamond” |  |  | 4 | 4 | [9 empty] | 230425 | bd |  | Grader, widened to 4m, bricks must be respored
| V0030 | Upper part of “Diamond” |  |  | 4 | 7 | [9 empty] | 230425 | bg |  | Grader, widened to 7m in parts!! erosion not stopped
| V0026 | Lower contour to Brandwacht |  |  | 4 | 6 | [9 empty] | 230425 | bf |  | Grader, widened to 6m in parts!!
| V0028 | Upper contour to Brandwacht |  |  | 5 | 5 | [9 empty] | 230425 | bh |  | Grader, widened to 5m
| V0030 upper | Steep upmountain to gumline |  |  | 4 | 4 | [9 empty] | 230425 | bi bj bk bl |  | Grader, more than 4m, steep, already erosion occurring
| V0030 upper | Steep upmountain to gumline | [13 empty] | 230425 | bm bn bo |  | Examples of erosion occurring within days after grading
| F369 gumline | [14 empty] | 230425 | bp bq br |  | Eucalyptus alien clearing along gumline
| F366 Fynbos | [14 empty] | 230425 | bs bt |  | A saligna untreated infestation (done with Tender 102)
| V0030 upper | Steep upmountain to gumline | [13 empty] | 230425 | bu |  | Fresh tracks of grader, disturbed loose soil
| V0026 | Lower contour to Brandwacht |  |  | 3 | 4 | [9 empty] | 230425 | bv bw |  | The grader itself, more than 3m wide
| V0024 | Main upmountain from Wateworks |  |  | 3 | 4 | [9 empty] | 230425 | bx |  | The grader itself, more than 3m wide
| V0021 | Entrance to waterworks |  |  | 3 | 4 | [9 empty] | 230425 | by |  | The grader itself, more than 3m wide
| V0020 upper | F369 norther border |  |  | 4 | 4 | [9 empty] | 230425 | bz ca cb |  | Grader, widened to 4m on steep slope, side disturbances
| V0022 | contour connector V0020 V0024 |  |  | 4 | 4 | [9 empty] | 230425 | cc cd |  | Grader, widened to 4m, side disturbances
| V0043 | Below dam fence |  |  | 4 | 4 | [9 empty] | 230425 | ce |  | Grader, widened to 4m, side disturbances
| V0052 | Connector V0044 V0043 |  |  | 4 | 4 | [9 empty] | 230425 | cf |  | Grader, widened to 4m, side disturbances
| B0133 | Main cycle line below dams |  |  | 4 | 4 | [9 empty] | 230425 | cg ch ci |  | Widened and badly eroded
| V0045 | South of Area A |  |  | 4 | 4 | [9 empty] | 230425 | cj |  | Grader, widened to 4m, side disturbances
| Area A | Area A Schuilplaats river | [13 empty] | 230425 | ck |  | Pinus canariensis invasion
| Area A | Area A Schuilplaats river | [13 empty] | 230425 | cl |  | A. mearnsii invasion
| Area A | Area A lower | [13 empty] | 230425 | cm |  | Pennisetium (kikuyu) covers large areas, also kweekgras, populus c
| B0135 lower | [14 empty] | 230425 |  |  | Lower part below V0045 does not exist
| B0136 | [14 empty] | 230425 | cn |  | No longer a footpath but jeep track, rename to V
| Area A | Area A lower | [13 empty] | 230425 | co |  | Thistle (there are at least 3 species)
| V0048 | Junction |  |  | 4 | 4 | [9 empty] | 230425 | cp |  | Grader, widened to 4m, side disturbances
| B0126 | Junction |  |  | 4 | 4 | [9 empty] | 230425 | cp |  | Grader, widened to 4m, side disturbances
| B0126 | Connector to V0044 |  |  | 4 | 4 | [9 empty] | 230425 | cq |  | Grader, widened to 4m, side disturbances
| v0050b | Gate-clubhouse lower | [13 empty] | 230506 | aa ab ac ad ae |  | Grader, widened to 4m, side disturbances
| V0051 | connector V0050 | [13 empty] | 230506 | af |  | Grader, widened to 4m, side disturbances
| v0050b | Gate-clubhouse lower | [13 empty] | 230506 | ag ah ai |  | endangered plant colony damaged
| FID087 | Main road up to clubhouse | [13 empty] | 230506 | aj |  | Grader activity, erosion stopped for the moment
| V0064 | Main road along fence |  |  | 4 | 4 | [9 empty] | 230506 | ak al |  | Grader, widened to 4m, side disturbances
| V0064/65 | Junction | [13 empty] | 230506 | am |  | Unchanged
| V0065 | Left branch off V0064 | [13 empty] | 230506 | an |  | Unchanged
| V0064 | Main road along fence | [13 empty] | 230506 | ao ap |  | Water pipe breather
| V064b | Road along fence, wetlands | [13 empty] | 230506 | aq ar as |  | Grader widened, water still runs on track
| Vxxxxx | Firebreak along fence | [13 empty] | 230506 | at |  | No code on trailmap
| V0064c | From wetlands to shooting range |  |  | 4 | 4 | [9 empty] | 230506 | au av |  | Grader, widened to 4m, side disturbances
| V0064c/V0068 | Junction | [13 empty] | 230506 | aw |  | Unchanged
| V0068a | Footpath eastwards | [13 empty] | 230506 | ax ay az |  | No longer jeeptrack, change code; erosion
| V0068a | Footpath eastwards | [13 empty] | 230506 | ba |  | Borehole graded area (2017)
| V0068b | Upper part above borehole | [13 empty] | 230506 | bb |  | Unchanged
| H0007 | Footpath towards H0006 |  |  | 1 | 1 | [9 empty] | 230506 | bc |  | Overgrown, some erosion
| B0164/H0005 | Junction | [13 empty] | 230506 | bd |  | Illegal new footpath (10m)
| Vvalley | Above cliffs | [13 empty] | 230506 | be |  | Hakea infestation
| Vvalley | Northern tributary of Blouklip | [13 empty] | 230506 | bf bg bh |  | Large A longifolia infestation
| V0040 lower |  |  |  | 4 | 4 | [9 empty] | 230610 | aa ab |  | Grader, widened to 4m, side disturbances
| V0042 |  |  |  | 1 | 1 | [9 empty] | 230610 | ac ad |  | Cycle track, no disturbance
| B0101 | Forbidden Fruits |  |  | 1 | 1 | [9 empty] | 230610 | ae |  | Unchanged
| B0123 | Cross connetcor |  |  | 1 | 1 | [9 empty] | 230610 | af |  | Unchanged
| B0051 |  |  |  | 4 | 4 | [9 empty] | 230610 | ag ah |  | Grader, widened to 4m, side disturbances
| V0041 |  |  |  | 4 | 4 | [9 empty] | 230610 | ai aj ak al |  | Grader, widened to 4m, side disturbances
| V0064 |  |  |  | 10 | 10 | [9 empty] | 230610 | am |  | Clubhouse, ground piles, usage unknown
| V0055lower |  |  |  | 5 | 5 | [9 empty] | 230610 | an ao |  | Grader, widened to 5m, side disturbances
| V0059 |  |  |  | 4 | 4 | [9 empty] | 230610 | ap aq ar |  | Grader, widened to 4m, side disturbances
| V0058 |  |  |  | 1 | 1 | [9 empty] | 230610 | as |  | Cycle track, no disturbance
[16 empty] | 230610 | at au |  | Southern Lobe overview
| V0063 |  |  |  | 1 | 1 | [9 empty] | 230610 | av |  | STF mainline track, no maintenance
[16 empty] | 230610 | aw |  | Sheepwalk North hakea infestation
| V0058 |  |  |  | 4 | 4 | [9 empty] | 230610 | ax |  | Grader, widened to 4m, side disturbances
| V0055 |  |  |  | 6 | 6 | [9 empty] | 230610 | ay az |  | Grader, widened to 6m, side disturbances
| V0032 |  |  |  | 4 | 4 | [9 empty] | 230610 | ba |  | Grader, widened to 4m, side disturbances
| V0031 | [14 empty] | 230610 | bb bc |  | Baboons
| V0030upper |  |  |  | 4 | 4 | [9 empty] | 230610 | bd be bf |  | Grader, widened to 4m, bad erosion
| V0028south |  |  |  | 4 | 4 | [9 empty] | 230610 | bg bh bi |  | Grader, widened to 4m, bad erosion
| V0028north |  |  |  | 3 | 4 | [9 empty] | 230610 | bl bm bn |  | Widened, some parts modified by STF unauthorised
| FID020 |  |  |  | 3 | 3 | [9 empty] | 230610 | bj |  | BAD EROSION
| FID139 |  |  |  | 3 | 3 | [9 empty] | 230610 | bk |  | BAD EROSION
| V0018 |  |  |  | 6 | 6 | [9 empty] | 230610 | bo bp bs |  | Grader, widened to 6m, bp shows where track narrows at end of grading
| xxx | [14 empty] | 230610 | bq br |  | Eucalyptus, Mearnsii not done See 230226 contractors track
| V0019 |  |  |  | 4 | 4 | [9 empty] | 230610 | bt bz |  | Unchanged
| F1049 |  |  |  | 8 | 8 | [9 empty] | 230610 | bu bv |  | F1049 Brandwacht NE boundary, 8m wide grading
| F1049 | [14 empty] | 230610 | bw |  | F1049 Brandwacht large Mearnsii stands
| F1049 |  |  |  | 8 | 8 | [9 empty] | 230610 | bx by |  | F1049 Brandwacht Southern boundary, 8m wide grading
| V0055highest | [14 empty] | 230610 |  |  | Unchanged
| V0026 |  |  |  | 4 | 4 | [9 empty] | 230610 | ca |  | Grader, widened to 4m, side disturbances
| V0033 |  |  |  | 4 | 4 | [9 empty] | 230610 | cb |  | Grader, widened to 4m, side disturbances
| V0037 |  |  |  | 5 | 5 | [9 empty] | 230610 | cc |  | Grader, widened to 5m, side disturbances

## Keys
Farm 366, 369 and 368/2 Road and Trail network
Key to profile entries
DRAFT 11 January 2023
| KEY | EXPLANATION
| Route code | Code as assigned by Schalk vd Merwe on 221122 (maybe needs updating, is certainly incomplete)
| Location | Very brief words describing location eg “below clubhouse”
| Type | V=”Motorised Vehicle Path”, B=”Bicycle path”, H=”Pedestrians only”
| Slope | 0=”essentially flat”, 1=”mild slope”, 2=”medium slope”, 3=”steep”, 4=”very steep”
| Width (metres) | Two numbers (minimum and maximum width of the path/trail)
| Erosion status | 0=”no erosion”, 1=”mild erosion”, 2=”5cm or deeper erosion”, 3=”deeper than 10cm” 4=”only 4x4 vehciles”, 5=”impassable”
| Current Usage | 0=”unused”, 1=”light use”, 2=”occasional use”, 3=”heavy use”
| Current Management Status | N=”nonexistent”, L=”Illegal route”, C=”exists but permanently closed”, R=”closed, currently under rehabilitation”, O=”open for use, good condition”, W=”open but needs work”
| Future Management Status | N=”nonexistent”, C=”should be closed”, R=”should be rehabilitated”, O=”should remain open”, W=”repair/maintenance work must be done”
| Responsible Party | M=”Stellenbosch Municipality”, F=”Stellenbosch Trail Fund”
| Rehabilitation Priority | 0=”Low priority”, 1=”medium priority”, 2=”high priority”
| On trailforks | 0=”no”, 1=”yes”
| On alltrails | 0=”no”, 1=”yes”
| Date of assessment | YYMMDD is the date on which the information above was entered